## Sheet1
Election Calendar for the Community of:
| Monday | Tuesday | Wednesday | Thursday | Friday
| 2022-09-19 | 2022-09-20 | 2022-09-21 | 2022-09-22 | 2022-09-23
PREPARATION OF
VOTERS LIST
(at least one week
Week 1 | before posting notice)
| 2022-09-26 | 2022-09-27 | 2022-09-28 | 2022-09-29 | 2022-09-30
| POST NOTICE OF |  | POST NOTICE OF
| VOTERS LIST/ |  | NOMINATIONS
| PERSONAL SECURITY |  | (at least seven days, but not
| PROTECTION |  | more than 21 days before
Week 2 | (at least four weeks before election day) |  | nomination period begins)
| 2022-10-03 | 2022-10-04 | 2022-10-05 | 2022-10-06 | 2022-10-07
NOMINATION
PERIOD BEGINS
Week 3 |  |  | (21st day before election day)
| 2022-10-10 | 2022-10-11 | 2022-10-12 | 2022-10-13 | 2022-10-14
|  |  | NOMINATION DAY | CANDIDATE | POST NOTICE OF
|  |  | (must be held on a date or dates | WITHDRAWAL | ELECTION
|  |  | during nomination period) | (up until 2 p.m. the | (within two days after
|  |  | 1 p.m. - 9 p.m. | day after nomination | period for withdrawal
|  |  |  | period ends) | expires)
|  |  | NOMINATION PERIOD |  | or
|  |  | ENDS |  | ACCLAMATION
(14th day before election day)
LAST DAY TO
Week 4 |  |  | REVISE VOTERS LIST
| 2022-10-17 | 2022-10-18 | 2022-10-19 | 2022-10-20 | 2022-10-21
ADVANCE VOTING
(anytime after ballots prepared
and no later than 48 hours before
election day)
Week 5 |  |  | 5 p.m. - 9 p.m.
| 2022-10-24 | 2022-10-25 | 2022-10-26 | 2022-10-27 | 2022-10-28
|  |  | ELECTION DAY | ANNOUNCE
|  |  | (fourth Wednesday in October) | RESULTS
Week 6 |  |  | 8 a.m. - 8 p.m. | (day after election)
SEO Signature
Formulas:
Tuesday = +[Monday]+1
Wednesday = +[Tuesday]+1
Thursday = +[Wednesday]+1
Friday = +[Thursday]+1